## WSJF Isoclines
Business Value | Time Criticality | Risk Reduction | COD | Job 1 | WSJF 1 | COD 2 | WSJF 2 | COD 3 | WSJF 3 | COD 4 | WSJF 4
|  |  | 2 | 1 | 2 | 8 | 8 | 34 | 34 | 89 | 89
|  |  | 2 | 4 | 0.5 | 8 | 2 | 34 | 8.5 | 89 | 22.25
|  |  | 2 | 8 | 0.25 | 8 | 1 | 34 | 4.25 | 89 | 11.125
|  |  | 2 | 12 | 0.16667 | 8 | 0.66667 | 34 | 2.8333 | 89 | 7.4167
|  |  | 2 | 16 | 0.125 | 8 | 0.5 | 34 | 2.125 | 89 | 5.5625
|  |  | 2 | 20 | 0.1 | 8 | 0.4 | 34 | 1.7 | 89 | 4.45
|  |  | 2 | 24 | 0.083333 | 8 | 0.33333 | 34 | 1.4167 | 89 | 3.7083

## Priorities
| Work Item Type |  |  | Cost of Delay Terms | [5 empty] | Priority
Epic | Work Item Use Case | Work Item User Story | Spike or Technical Work Item | User Business Value | Project Value | Time Criticality | RR ¦ OE | CoD | Job Size (user story points) | WSJF | Priority | Planned Iteration
Resist | Control Resistance | Provide basic resistance |  | 55 | 1 | 21 | 1 | 78 | 55 | 1.4182 | 1.4182
Resist | Control Resistance | Set resistance under rider control |  | 13 | 1 | 5 | 1 | 20 | 21 | 0.95238 | 0.95238
Resist | Control Resistance | Set resistance under external control |  | 21 | 1 | 5 | 1 | 28 | 39 | 0.71795 | 0.71795
Resist | Control Resistance | ERG Mode |  | 21 | 1 | 1 | 1 | 24 | 55 | 0.43636 | 0.43636
Set up Physical Bike | Set up Bike Fit | Adjust handlebar reach |  | 5 | 1 | 1 | 3 | 10 | 3 | 3.3333 | 3.3333
Set up Physical Bike | Set up Bike Fit | Adjust handlebar height |  | 8 | 1 | 1 | 3 | 13 | 3 | 4.3333 | 4.3333
Set up Physical Bike | Set up Bike Fit | Adjust seat reach |  | 13 | 1 | 8 | 13 | 35 | 3 | 11.6667 | 11.6667
Set up Physical Bike | Set up Bike Fit | Adjust seat height |  | 13 | 1 | 13 | 13 | 40 | 3 | 13.3333 | 13.3333
Set up Physical Bike | Set up Bike Fit | Select crank length |  | 2 | 1 | 1 | 2 | 6 | 5 | 1.2 | 1.2
Set up Physical Bike | Estimate bike fit with external parameters | Load GURU bike fit data |  | 5 | 1 | 1 | 2 | 9 | 13 | 0.69231 | 0.69231
Set up Physical Bike | Estimate bike fit with external parameters | Load Trek Bike Fit data |  | 5 | 1 | 1 | 2 | 9 | 13 | 0.69231 | 0.69231
Set up Physical Bike | Estimate bike fit with external parameters | Compute fit from professional fit data |  | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 6
Set up Physical Bike | Predict bike fit with camera image | Access camera image |  | 5 | 1 | 1 | 1 | 8 | 2 | 4 | 4
Set up Physical Bike | Predict bike fit with camera image | Retrieve road bike dimensions from camera image |  | 8 | 1 | 1 | 1 | 11 | 5 | 2.2 | 2.2
Set up Physical Bike | Predict bike fit with camera image | Compute fit parameters from road bike dimensions |  | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 2
Set up Physical Bike | Manually Adjust Bike Fit |  |  | 34 | 1 | 21 | 1 | 57 | 13 | 4.3846 | 4.3846
|  |  | Spike: Robustness of main motor | 34 | 1 | 1 | 34 | 70 | 5 | 14 | 14
|  |  | Spike: Agile MBSE Impact | 1 | 34 | 21 | 13 | 69 | 3 | 23 | 23
|  |  | Spike: USB Robustness | 21 | 8 | 1 | 8 | 38 | 5 | 7.6 | 7.6
|  |  | Spike: Aggressive Schedule | 1 | 1 | 34 | 34 | 70 | 3 | 23.3333 | 23.3333
|  |  | Spike: Motor response lag time | 8 | 1 | 1 | 1 | 11 | 8 | 1.375 | 1.375
|  |  | Spike: Team Availability | 1 | 55 | 1 | 21 | 78 | 2 | 39 | 39
Communicate with Apps | Communicate with low power Bluetooth |  |  | 55 | 1 | 8 | 1 | 65 | 34 | 1.9118 | 1.9118
Communicate with Apps | Communicate with ANT+ |  |  | 34 | 1 | 5 | 1 | 41 | 34 | 1.2059 | 1.2059
Communicate with Apps | Communicate with ANT FEC |  |  | 34 | 1 | 13 | 1 | 49 | 55 | 0.89091 | 0.89091
Configure Bike for Rider | Connect personal data to app |  |  | 13 | 1 | 1 | 1 | 16 | 21 | 0.7619 | 0.7619
|  | Calibrate Power Output |  | 8 | 8 | 21 | 1 | 38 | 8 | 4.75 | 4.75
| Manage personal data |  |  | 21 | 3 | 2 | 1 | 27 | 5 | 5.4 | 5.4
Monitor Ride Metrics |  | Monitor Power |  | 34 | 1 | 1 | 1 | 37 | 13 | 2.8462 | 2.8462
Monitor Ride Metrics |  | Monitor Speed |  | 21 | 1 | 1 | 1 | 24 | 5 | 4.8 | 4.8
Monitor Ride Metrics |  | Monitor Distance |  | 21 | 1 | 1 | 1 | 24 | 5 | 4.8 | 4.8
Monitor Ride Metrics |  | Monitor Incline |  | 13 | 1 | 1 | 1 | 16 | 8 | 2 | 2
Monitor Ride Metrics |  | Monitor Cadenace |  | 8 | 1 | 1 | 1 | 11 | 5 | 2.2 | 2.2
Emulate Gearing | Emulate Basic Gearing |  |  | 34 | 1 | 34 | 1 | 70 | 89 | 0.78652 | 0.78652
Emulate Gearing | Emulate Front and rear gearing |  |  | 34 | 1 | 21 | 1 | 57 | 34 | 1.6765 | 1.6765
Emulate Gearing | Emulate mechanical gearing |  |  | 21 | 1 | 21 | 1 | 44 | 34 | 1.2941 | 1.2941
Emulate Gearing | Emulate DI2 gearing |  |  | 13 | 1 | 5 | 1 | 20 | 55 | 0.36364 | 0.36364

## Priorities (2)
| Work Item Type |  |  | Cost of Delay Terms | [5 empty] | Priority
Epic | Work Item Use Case | Work Item User Story | Spike or Technical Work Item | User Business Value | Project Value | Time Criticality | RR ¦ OE | CoD | Job Size (user story points) | WSJF | Priority | Planned Iteration
|  |  | Spike: Team Availability | 1 | 55 | 1 | 21 | 78 | 2 | 39 | 39 | 0
|  |  | Spike: Aggressive Schedule | 1 | 1 | 34 | 34 | 70 | 3 | 23.3333 | 23.3333 | 0
|  |  | Spike: Agile MBSE Impact | 1 | 34 | 21 | 13 | 69 | 3 | 23 | 23 | 0
Resist | Control Resistance | Provide basic resistance |  | 55 | 1 | 21 | 1 | 78 | 55 | 1.4182 | 1.4182 | 1
|  |  | Spike: Motor response lag time | 8 | 1 | 1 | 1 | 11 | 8 | 1.375 | 12 | 1
|  |  | Spike: Robustness of main motor | 34 | 1 | 1 | 34 | 70 | 5 | 14 | 14 | 1
Set up Physical Bike | Set up Bike Fit | Adjust seat height |  | 13 | 1 | 13 | 13 | 40 | 3 | 13.3333 | 13.3333 | 1
Set up Physical Bike | Set up Bike Fit | Adjust seat reach |  | 13 | 1 | 8 | 13 | 35 | 3 | 11.6667 | 11.6667 | 2
|  | Calibrate Power Output |  | 8 | 8 | 21 | 1 | 38 | 8 | 4.75 | 10 | 2
Emulate Gearing | Emulate Front and rear gearing |  |  | 34 | 1 | 21 | 1 | 57 | 34 | 1.6765 | 19 | 2
Emulate Gearing | Emulate mechanical gearing |  |  | 21 | 1 | 21 | 1 | 44 | 34 | 1.2941 | 10 | 2
Emulate Gearing | Emulate Basic Gearing |  |  | 34 | 1 | 34 | 1 | 70 | 89 | 0.78652 | 10 | 2
Set up Physical Bike | Manually Adjust Bike Fit |  |  | 34 | 1 | 21 | 1 | 57 | 13 | 4.3846 | 4.3846 | 3
Set up Physical Bike | Set up Bike Fit | Adjust handlebar height |  | 8 | 1 | 1 | 3 | 13 | 3 | 4.3333 | 4.3333 | 3
Set up Physical Bike | Set up Bike Fit | Adjust handlebar reach |  | 5 | 1 | 1 | 3 | 10 | 3 | 3.3333 | 3.3333 | 3
Monitor Ride Metrics |  | Monitor Power |  | 34 | 1 | 1 | 1 | 37 | 13 | 2.8462 | 2.8462 | 3
Monitor Ride Metrics |  | Monitor Speed |  | 21 | 1 | 1 | 1 | 24 | 5 | 4.8 | 4.8 | 3
Monitor Ride Metrics |  | Monitor Distance |  | 21 | 1 | 1 | 1 | 24 | 5 | 4.8 | 4.8 | 3
|  |  | Spike: USB Robustness | 21 | 8 | 1 | 8 | 38 | 5 | 7.6 | 7.6 | 3
Monitor Ride Metrics |  | Monitor Cadence |  | 8 | 1 | 1 | 1 | 11 | 5 | 2.2 | 2.2 | 4
Communicate with Apps | Communicate with low power Bluetooth |  |  | 55 | 1 | 8 | 1 | 65 | 34 | 1.9118 | 1.9118 | 4
Set up Physical Bike | Set up Bike Fit | Select crank length |  | 2 | 1 | 1 | 2 | 6 | 5 | 1.2 | 1.2 | 4
Resist | Control Resistance | Set resistance under rider control |  | 13 | 1 | 5 | 1 | 20 | 21 | 0.95238 | 1 | 4
Configure Bike for Rider | Connect personal data to app |  |  | 13 | 1 | 1 | 1 | 16 | 21 | 0.7619 | 1 | 4
Set up Physical Bike | Estimate bike fit with external parameters | Compute fit from professional fit data |  | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 0.5 | 5
Monitor Ride Metrics |  | Monitor Incline |  | 13 | 1 | 1 | 1 | 16 | 8 | 2 | 0.5 | 5
Communicate with Apps | Communicate with ANT+ |  |  | 34 | 1 | 5 | 1 | 41 | 34 | 1.2059 | 0.5 | 5
Communicate with Apps | Communicate with ANT FEC |  |  | 34 | 1 | 13 | 1 | 49 | 55 | 0.89091 | 0.89091 | 5
Set up Physical Bike | Estimate bike fit with external parameters | Load GURU bike fit data |  | 5 | 1 | 1 | 2 | 9 | 13 | 0.69231 | 0.69231 | 5
Set up Physical Bike | Estimate bike fit with external parameters | Load Trek Bike Fit data |  | 5 | 1 | 1 | 2 | 9 | 13 | 0.69231 | 0.69231 | 5
Resist | Control Resistance | ERG Mode |  | 21 | 1 | 1 | 1 | 24 | 55 | 0.43636 | 0.3 | 5
| Manage personal data |  |  | 21 | 3 | 2 | 1 | 27 | 5 | 5.4 | 0.3 | 6
Set up Physical Bike | Predict bike fit with camera image | Access camera image |  | 5 | 1 | 1 | 1 | 8 | 2 | 4 | 0.3 | 6
Set up Physical Bike | Predict bike fit with camera image | Retrieve road bike dimensions from camera image |  | 8 | 1 | 1 | 1 | 11 | 5 | 2.2 | 0.3 | 6
Set up Physical Bike | Predict bike fit with camera image | Compute fit parameters from road bike dimensions |  | 1 | 1 | 1 | 1 | 4 | 2 | 2 | 0.3 | 6
Resist | Control Resistance | Set resistance under external control |  | 21 | 1 | 5 | 1 | 28 | 39 | 0.71795 | 0.3 | 6
Emulate Gearing | Emulate DI2 gearing |  |  | 13 | 1 | 5 | 1 | 20 | 55 | 0.36364 | 0.3 | 6

## Missions
Release Plan | Iteration 0 | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
Functionality |  | Initial Frame Mockup Basic Motor Electronics Basic Rider Controls Basic Resistance | Set Up Bike Fit (seat) Basic Digital Electronics Calibrate Power Output Basic gearing | Set up Bike Fit (handlebars) Manually adjust bike fit Monitor Power | Set up Bike Fit (Cranks) Monitor Speed Monitor Distance Bluetooth Monitor Cadence Data to App connect | Bike fit with external parameters Motorized Incline Monitor Incline ANT+ ANT FEC | Manage personal data Predict Bike with Camera Image External Resistance control ERG Mode
Target Platforms |  | Hand build mechanicals Hand built analog electronics Simulated digital electronics | Basic Hand built Mechanicals Hand built electronics | Prototype mechanicals for manufacturing | First run factory electronics | First run mechanicals | 2nd run factory electronics 2nd run factory mechanicals
Technical Work Items |  | Analyze frame stability and strength Refine SW/EE deployment architecture | Design cable runs Analyze electrical power needs Add in SW concurrency architecture | Add in SW Distribution Framework | Finalize fly wheel mass | EMI Conformance testing
Spikes | Team Availability Aggressive Schedule Agile MBSE Impact | Motor Response Time | Robustness of main motor | USB Robustness
Defects